## App Enhancement Requests
# | Enhancement description | MassLight Hrs. Estimate | Notes | AARP Priority | Reponsible Groups
Test 1 | Recreation of blank feedback issue Goal of identifying reliable method of reproducing issue to allow for subsequent identification of solution to said issue |  |  |  | ML
Fix 1 | Identification and implementation of technical solution for blank feedback issue |  |  |  | ML
Enhancement 1 | Include a screen after sending feedback confirming that the feedback has been submitted successfully. Pilot feedback: users were not sure if their feedback had been successfully transmitted. |  | Would likely be 3 variations: • Successful Send • Successful Queue • Error |  | ML
Enhancement 2 | Include the AARP toll free number in the Settings screen. This should link to the native phone application - Click to Call Pilot feedback: (Martha)Nice to have in case someone needs immediate attention and the user doesn’t remember the Contact Center number. |  |  |  | ML
Enhancement 3 | Include the “Help” link that currently links to the tutorial screens on every page. Feedback: Users would like to access the instructions at any point during their transaction. |  |  |  | ML
Enhancement 4 | On the Home Screen - Include CTA to bulls eye, i.e., Click here to enter feedback Feedback: It was not clear to some user's that they needed to click on the bulls eye to enter their feedback. |  |  |  | ML
Enhancement 5 | Logout option should also be included on the last page/confirmation or separately, instead of having to go to Settings to logout OR Add text in the upfront tutorial explaining that the user will remain logged in until they elect to logout. Feedback: Some users were not sure if they could leave the App without logging out and be able to access the feedback screen again without logging back in. |  |  |  | ML
Enhancement 6 | On the login screen – change text from Email Address to AARP Membership Email Address Feedback: This will make sure people know exactly which email address to use. There was confusion about this. |  |  |  | ML
Enhancement 7 | On the feedback screen, Under Event, State Office, Word of Mouth – the selected option needs to be highlighted or the unselected one’s made lighter. Feedback: It was not clear which one was selected as they were all highlighted. |  |  |  | ML
Enhancement 8 | Include instruction – Click for dictation on keyboard, perhaps a hover state above the microphone OR Add language and imagery to clarify this to the tutorial screen. Feedback: Some people didn’t know where to click for this. |  |  |  | ML
Enhancement 9 | On the Feedback screen, include verbiage to change "Event" to "AARP Event" Feedback: Some feedback received suggested that users may have thought that the event was any event and not specific to AARP related events. |  | *This is assumed to be a front-end only change and that the info passed on the back end would not need to be updated to reflect 'AARP Event' instead of the current name of simply, 'Event' |  | ML
Enhancement 10 | Remove the “Skip” option from the instructions following each login. Feedback: Some users had questions that would have been answered had they fully read the instructions. It’s just 4 screens, and we need to encourage users to use the app as intended. |  | *It is assumed that this means that each time a user logs in, they will be forced to go through the entire instructions flow. |  | ML
Enhancement 11 | Include the App version number in the Settings screen so that users will know if they’re using the latest version. Pilot feedback: Unclear if users need to delete the old App version to install the new one. I had to delete mine and install the new version. |  |  |  | ML
Enhancement 12 | Develop authentication process to replace the Employee and Volunteer four digit codes. Pilot feedback: Entering the V/E code appears to be a barrier. A couple of the testers mentioned they would prefer not having to enter their 4 digit code every time they logout and back in again; they’re unlikely to remember it. |  |  |  | DSM, ITS, ML
Enhancement 13 | Optimize App for any smart phone device Pilot feedback: One user was unable to download App on an older iPad version; we may need to optimize for any iOS or Android smart device. |  |  |  | ML

## Issue Log
Issue# | Outstanding issues | Status | Group(s) Responsible | Priority # | Resolved | Resolve Date
1 | All App feedback should have a Source of "Frontline Feedback". Instead, this field is being populated with "Not Specified" | 9/28/16 AKQA - Blank SOURCE Field – confirmed that this field was left blank intentionally and at the direction of Clarabridge via their last email prior to delivery of the app (i.e. the late Friday,9/9 email from Clarabridge with the ‘workaround’ that we implemented in build 19). Unfortunately, using the default SOURCE attribute was causing an indexing issue on the with the Clarabridge dashboard where the data wouldn’t appear properly. Instead, Clarabridge created an entirely new attribute named SOURCE_FRONTLINE. Unfortunately, until Clarabridge fixes their indexing issue, we won’t be able to populate information into that field 9/29/16 AKQA will speak with Clarabridge about the SOURCE workaround and ask whether they’ve fixed the indexing issue. 9/30/06 Clarabridge(John Hertel) opened up separate tickets with their advanced support team to work these issues. Next Steps: After sepaking with CB, AKQA can fix the issue 10/11/16 AKQA provided estimate for the fix along with enhancements 10/12/16 Eileen and JK met with AKQA and authorized them to move forward with this fix. 10/25/16 AKQA notified AARP of fix. New App version 3.22 deployed. | AKQA | 3 | Y | 2016-10-27
2 | Feedback with no verbatim (body text) should not be passed into Clarabridge. Seeing multiple instances where the feedback is being lost during transmission from AKQA to Clarabridge. | 9/30/16 AKQA - It looks like all of the feedback issues are stemming only from iOS devices. 10/3/16 AKQA to reach out to Clarabridge to determine if they show the feedback being transmitted to them on the back-end. 10/4/16 Clarabridge notified AKQA that they checked and could see data is not fed in the system. This would seem to suggest that the feedback itself is not reaching Clarabridge. Next steps: To troubleshoot, Clarabridge has asked AKQA to share the process they're using to submit the feedback. AKQA hoping to schedule a call on 10/5 or 10/6 with Clarabridge to discuss with technical counterparts. AKQA still diagnosing where this issue is happening and hope to have an understanding by end of week, 10/7. Clarabridge stress tested their API and found no issue. AKQA will need to test their end to determine root cause. Time required to test and fix is over alloted mainteance hrs. therefore this will be addressed by ML. | ML and Clarabridge | 2 | N
3 | Keyboard Not Appearing on some devices when users attempt to enter feedback | 9/28/16 AKQA has confirmed that this is occurring on iOS 10 (the newly released iPhone operating system). Before they determine how to address it, they’ll need to identify whether it exists on iOS 9. iOS 9 is the operating system that AARPx agreed to support as part of our device and OS matrix. They’re going to take an hour or two to troubleshoot. 9/29/16 AKQA - Confirmed that this is a persistent issue on all iOS operating systems. Next steps: AKQA will get back to us shortly with an estimate of hours to have our Developer look into this. After sepaking with CB, AKQA can fix the issue 10/11/16 AKQA provided estimate for the fix along with enhancements 10/12/16 Eileen and JK met with AKQA and authorized them to move forward with this fix. 10/25/16 AKQA notified AARP of fix. New App version 3.22 deployed. | AKQA | 1 | Y | 2016-10-25

## User Guide Enhancements
Enhancement # | Include in user guidelines | Group(s) Responsible | Priority #
1 | Include instructions that user can remain logged in and NOT necessary to log out after feedback submission. Pilot feedback: There was some confusion as to whether users should logout after using the app, or if there is any harm in staying logged in. Preference was to remain logged in, but they didn’t know if there were negative repercussions in doing so. | AARPx Insights & Listening
2 | Include instructions that the code being requested is the 4 digit E/V code and not the user's device password. Pilot feedback: Some users were not sure if the code being requested was their personal phone password used to unlock their phone or the V/E code. Need to clarify this in the instructions if we continue with the code. | AARPx Insights & Listening
3 | Include instructions on how users can allow the download of third party apps on their mobile devices. Pilot feedback: Some users didn't know how to enable 3rd party Apps on their devices.This was restricted. | AARPx Insights & Listening
4 | Include in instructions that each person’s comment(s) should be a separate submission. This will help us track the number of comments captured. Pilot feedback: Clarity around submission of feedback required. Question arose regarding entering feedback from multiple people as one submission during an event. | AARPx Insights & Listening
5 | Include App information on the VOC page on Infonet. Include user guide, reiterate the E/V code to be used(if still required), App download instructions etc. Have a troubleshooting hotline that users can call if having issues downloading the App. Pilot feedback: Michelle M. suggested inclusion of this as was not sure where to go for assistance. Both Joan and Martha experienced trouble downloading the App. | AARPx Insights & Listening (After tranision this would be managed by DSM)